## Sheet1
March 31st, 2004: |  | CAPITAL PLAN FOR BUILDINGS and PROJECTS in EXCESS of $2M and OTHER REQUIREMENTS. MASTER LIST March 31st, 2004.
Summary Sheet, Page 1
Table 1: SUMMARY OF CURRENT CAPITAL PLAN | [11 empty] | [all funds in Millions of dollars]
[9 empty] | Expected Internal Financing [Debt Repayment Sources] | [5 empty] | Contingency Internal Financing
SUMMARY DATA FOR SECTION 1 | [5 empty] | Total Project Cost | Funding Available, all Sources | Borrowing Required [I=G-H] | UIIF | EGF [UTM & UTSC] | Division | Student Levy Revenues | Residence & Ancillary Revenues | Other Central Funds | Funding Gap
[6 empty] | G | H | I = J+L+M+N+O+P+Q | J | L | M | N | O | P | Q
COMPLETED CURRENT CAPITAL PLAN |  |  |  | Section 1a |  | 351.29 | 96.665 | 254.625 | 76.97 | 1.31 | 19.81 | 0 | 155.81 | 0 | 0.72
PROJECTS UNDER CONSTRUCTION OR BEING ACQUIRED |  |  |  | Section 1b |  | 324.203 | 187.011 | 137.192 | 19.9237 | 23.96 | 1.6556 | 6.9493 | 54.8494 | 0 | 29.86
PROJECTS AT PRE-TENDER OR AT TENDER STAGE |  |  |  | Section 1c |  | 135.9764 | 54.2844 | 81.692 | 8.05 | 23.206 | 8.971 | 16 | 14.165 | 0 | 11.3
Total for CURRENT CAPITAL PLAN | [5 empty] | 811.4694 | 337.9604 | 473.509 | 104.9437 | 48.476 | 30.4366 | 22.9493 | 224.8244 | 0 | 41.88
Table 2: OTHER REQUIREMENTS | [11 empty] | [all funds in Millions of dollars]
OTHER REQUIREMENTS: SECTION 2 | [5 empty] | Total Cost | Funding Available, all Sources | Borrowing in addition to Capital Plan | UIIF | EGF | Division | Student Levy Revenues | Residence & Ancillary Revenues | Other Central Funds | Funding Gap
EXISTING |  |  |  | Section 2a
UIIF Tranche #1 |  |  | 30 |  | Capital Plan
UIIF Tranche #2 |  |  | 30 |  | Capital Plan
UIIF Tranche #4 [re: 2003/04 operating Budget] |  |  | 19.7 |  | Capital Plan
| Other Requirements |  |  |  |  | 98.872 |  | 98.872 |  |  | 9.262 | 2.43 | 70.73 | 16.45 | 0
| Endowment Matching Funds [Not Capital Plan] |  |  |  |  | 36.5 |  | 36.5
PLANNED |  |  |  | Section 2b
UIIF Tranche # 3 |  |  | 30 | 24.19 | Capital Plan
EGF: |  |  | 55.08 | 45.62 | Capital Plan
| UIIF : Not Capital Plan |  |  |  |  | 5.81 |  | 5.81 | 5.81
| EGF: Available for Capital Plan |  |  |  |  | 6.61 |  | 6.61 |  | 6.61
| Endowment Matching Funds [Not Capital Plan] |  |  |  |  | 7.5 |  | 7.5 | [5 empty] | 44
Total for OTHER RERQUIREMENTS | [5 empty] | 155.292 |  | 155.292 | 5.81 | 6.61 | 9.262 | 2.43 | 70.73 | 60.45 | 0
TOTAL: CAPITAL PLAN & OTHER REQUIREMENTS | [5 empty] | 966.7614 | 337.9604 | 628.801 | 110.7537 | 55.086 | 39.6986 | 25.3793 | 295.5544 | 60.45 | 41.88
Changes from Past Record
|  | January 31st. 2004 |  |  |  | 965.76 |  | 627.8
| 1 |  | Library Storage Facility |  |  | 1 |  | 1 |  | $1M of the $6M project cost approved by BB on March 1st, 2004.
|  | March 1st, 2004 |  |  |  | 966.76 |  | 628.8
Additional items pending for approval:
| 1 |  | Economics Building |  |  | -8 |  | -8 |  | Reduce cost by $8 million: Phase 2 will not be constructed.
|  | May 2004 projected |  |  |  | 958.76 |  | 620.8

## Sheet2
CAPITAL PLAN FOR BUILDINGS and PROJECTS in EXCESS of $2M: March 31st, 2003.
MASTER COPY: March 31st, 2004.
SECTION 1: CURRENT CAPITAL PLAN: Three sections, SECTIONS 1a, 1b & 1c
Sector Descriptor | [5 empty] | Expected Internal Financing | [6 empty] | Contingency Internal Funding | Expenditure Status
[Debt Replacement Sources]
Projects in Section 1a are nearing completion. Sections 1b and 1c will proceed expeditiously to completion and implementation respectively./ Any ultimate shortfall in funding will be met from University funds, except for those projects marked with an asterisk./ Projects are all approved by GC./ All projects assigned an A1 priority A1. / A1A, indicates that the project is also identified with Advancement for fund raising. |  | Priority | Current Cost | Funds Available: Donations, CFI, Super Build, OIT , FRP, Interest, Faculty Cash etc | Equity UIIF Cash | UIIF Funds | Enrolment Growth Funds | Division | Student Levy Funds | Residences & Ancillaries Funding | Other Central Funds | Equity | Funding Gap | Approved Expenditure to Date | Cost Committed to Date | $ Paid to Date | Build: Start date | Advancement Targets | Donors Secured Support |  | Notes
|  |  | F | G | AW | I | J | K | L | M | N | P | P
SECTOR | SECTION 1a: COMPLETED PROJECTS WITHIN THE CURRENT CAPITAL PLAN
UTSC: | Residence Phase 4 | A1 | 16.26 | 0 | 0 | 0 | 0 | 0 | 0 | 16.26 | 0 | 0 | 0 | 14.9 | 13.82 | 5.04 | 2002-05-02
UTM: | CABB- Centre for Applied Biosciences & Biotechnology | A1 | 3.39 | 2.08 | 0 | 0 | 1.31 | 0 | 0 | 0 | 0 | 0 | 0 | 3.39 | 3.39 | 3.39 | 2002-05-01
UTM: | Residence Phase 7 | A1 | 15.32 | 0 | 0 | 0 | 0 | 0 | 0 | 14.6 | 0 | 0 | 0.72 | 14.6 | 13.64 | 8.38 | 2002-05-02
Health Sciences: | Renovation of 500 University Ave/Centre for | A1A | 11.12 | 0.7 | 0 | 10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.12 | 9.816 | 8.523 | 2002-03-02 | 16 | 0 |  | $ 11.12 is being recovered from the Faculty of Medicine
FASE/A&Sc: | BCIT - Bahen Centre for Information Technology | A1A | 111.87 | 73.44 | 0 | 18.62 | 0 | 19.81 | 0 | 0 | 0 | 0 | 0 | 108.81 | 110.612 | 110.593 | 1999-11-01 | 17.9 | 20.52 |  | $1.9M is the cost shared by Provost & V-P Business
Arts & Science | Growth Facility for Plant Research(Earth Sciences) | A1 | 6.07 | 6.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.07 | 5.962 | 5.838 | 2001-09-01
Arts & Science: | Sidney Smith Infill Phases 1 ($1.844M) & 2 | A1 | 3.08 | 1.075 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08 | 2.455 | 1.109 | 2002-06-01
Other Faculties | Library: Morrison Pavilion, Gerstein Science Information Centre | A1A | 15.19 | 6.36 | 0 | 8.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.19 | 15.075 | 14.363 | 2001-08-01 | 6.36 | 6.36
Campus: | Early Learning Centre [Childcare Facilities] | A1 | 4.3 | 0 | 0 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3 | 3.88 | 1.65 | 2002-06-02
Campus: | Purchase of the Board of Education | A1 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17
Campus: | Purchase of Colony Hotel: 89 Chestnut Street Upgrade | A1 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 72 | 72
Campus: | South East Infrastructure | A1 | 3.77 | 3.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 7.88 | 0.36 | 2002-03-02
Campus: | Purchase of 500 University | A1 | 15.8 | 0 | 0 | 15.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8 | 15.8
Campus: | Purchase of Medical Arts Building | A1 | 14.26 | 0 | 0 | 0 | 0 | 0 | 0 | 14.26 | 0 | 0 | 0 | 14.26 | 14.26
Campus: | Parking Garage: BCIT | A1 | 13.1 | 2.07 | 0 | 0 | 0 | 0 | 0 | 11.03 | 0 | 0 | 0 | 13.1 | 12.7 | 12.12 | 1999-11-01
Campus: | New College Residence | A1 | 26.76 | 1.1 | 0 | 0 | 0 | 0 | 0 | 25.66 | 0 | 0 | 0 | 26.76 | 21.49 | 11.52 | 2002-04-02 |  |  |  | $352k/yr 8yrs APF /College 0.75M A&S .35M
TOTAL | SECTION 1a: Total |  | 351.29 | 96.665 | 0 | 76.97 | 1.31 | 19.81 | 0 | 155.81 | 0 | 0 | 0.72 | 327.15 | 339.78 | 182.886 | 446101 | 40.26 | 26.88
SECTOR | SECTION 1b: PROJECTS UNDER CONTRUCTION or BEING ACQUIRED WITHIN THE CURRENT CAPITAL PLAN
UTSC: | ARC - Academic Resource Centre | A1A | 20.26 | 12.24 | 0 | 0 | 7.34 | 0 | 0 | 0 | 0 | 0 | 0.69 | 22.56 | 17.423 | 4.751 | 2002-06-01 | 11 | 0 |  | $0.69M shortfall. Aug 03 [G: 6.38 to 11.04] [J:11.99 to 7.34]. SuperBuild 20 02 project.
UTSC: | Parking & Roadway Improvements | A1 | 10.11 | 2.31 | 0 | 0 | 0 | 0 | 0 | 7.798 | 0 | 0 | 0 | 10.15 | - | - | 2003-05-01 |  |  |  | $184k from ARC; $232k from Parking Anc.; $1.9 from Right-of- Way [$1.11M + $0.79M].
UTSC: | Student Centre | A1A | 13.923 | 1.25 | 0 | 4.7237 | 0 | 0 | 6.9493 | 0 | 0 | 0 | 1 | 1 | 0.85 | 0.3 |  |  |  |  | $1.25 + $6.95 totals the $8.2M ancillary loan
UTSC: | Management Building | A1A | 15.43 | 9.8 | 0 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 1.16 | 15.53 | 1.011 | 0.219 | 2003-06-01 | 1.16-3.5 | 0 |  | $1.16M backed by EGF. Aug. 03 [G: 0.0 to 9.8], [J: 14.37 to 5.73]. SuperBuild 2002 project
UTM: | CCIT Communication, Culture & Information Technology | A1A | 34.67 | 24.02 | 0 | 2.5 | 8.15 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 3.1 | 1.697 | 2002-06-02 | 11 | 0.5 |  | $50k fundrairing not added
UTM: | CCIT Parking | A1 | 12.892 | 0 | 0 | 0 | 0 | 0 | 0 | 12.89 | 0 | 0 | 0 | 12.7 | 6.41 | 3.76 | 2002-05-02 |  |  |  | P&B $12.700M. BB $12.892M
Health Sciences: | CCBR with shelled floors | A1A | 87.6 | 70.69 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 14.11 | 10 | 8.381 | 2.834 | 2003-03-01 | 25 | 5 |  | $2.4M in 70.69M to be clarified
Health Sciences: | Leslie L. Dan Pharmacy Building | A1A | 75 | 55.8 | 0 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 10 | 7.837 | 1.623 | 2003-05-01 | 12 | 22 |  | Greenhouse cost is $1.035M. [P&B: $70M to $71.4M], [Jun. 19, 2003, BB approves $75M]
Arts & Science: | Lash Miller Undergraduate Chemistry Laboratories | A1 | 5.6 | 1.6 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003-06-01 |  |  |  | Supported by EGF
Other Faculties: | Rotman Expansion: 4th & 5th floors | A1A | 4.318 | 4.318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003-08-01 |  |  |  | Tender price is $4,318,000. Reduced from original $4,400,000 by $82,000
Other Faculties: | *SCS: Community Learning Renovation | A1A | 7.1 | 0.9 | 0 | 0 | 0 | 0 | 0 | 5.3 | 0 | 0 | 0.9 | 7.1 | 1.167 | 0.3569 | 2003-06-01 | 2.5 |  |  | [H: 0.0 to 0.90], [M: 4.6 to 5.3], [P: 2.6 to 0.9]. Approved by V-Ps in August, 2003
Campus: | King's College Road Open Space Plan | A1A | 5.3 | 2.4 | 0 | 2.7 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 4.6 |  |  | 2002-10-01 |  |  |  | SUMMER AUTHORITY 2003 [0.2M from FASE, 0.5M from Advancement]
Residence: | Woodsworth College Residence | A1 | 32 | 1.683 | 0 | 0 | 0 | 1.4556 | 0 | 28.8615 | 0 | 0 | 0 | 31.84 | 5.33 | 2.45 | 2002-12-03 |  |  |  | $1.4556116M [$0.876M Library; $0.181M Rotman. $0.398843M Commerce]
TOTAL | SECTION 1b: Total |  | 324.203 | 187.011 | 0 | 19.9237 | 23.96 | 1.6556 | 6.9493 | 54.8494 | 0 | 0 | 29.86
SECTOR | SECTION 1c: PROJECTS AT PRE TENDER OR AT TENDER STAGE
UTSC: | Phase 1: Science Laboratories Upgrade at UTSC | A1 | 4.3 | 1.83 |  | 0 | 2.47 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | SuperBuild 2002 project. Other support from EGFFunding.
UTSC: | Arts Classroom Building | A1A | 20.38 | 12.62 |  | 0 | 7.76 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | SuperBuild 2002 project. Other support from EGFFunding.
UTM: | Alumni Gates [Collegeway] + Alumni House [Springbank] | A1A | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2003-05-01 |  |  |  | $1M directed to Alumni House [Springbank], balance of $1.5M for Alumni Gates [Collegeway access]
UTM: | Wellness Centre | A1 | 24.5 | 0 | 0 | 7 | 0 | 0 | 16 | 0 | 0 | 0 | 1.5
UTM: | Academic Learning Centre | A1A | 34 | 26.824 |  | 0 | 7.176 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 9 |  |  | SuperBuild 2002 Project. Other support from EGF.
Arts & Science: | Economics Building | A1A | 14.3 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 8.3 | 0 | 0 | 0 | 2004-12-01
Arts & Science: | Sidney Smith Patio | A1 | 3.3 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0
Other Faculties: | Woodsworth Basement & 1st Floor | A1A | 3.6964 | 0.7254 |  | 0 | 0 | 2.971 | 0 | 0 | 0 |  | 0 | [7 empty] | Woodsworth Residence. Classroom & Audio Visual Storage + Commerce Career Centre & Aid Centre
Other Faculties: | LIBRARY: Library Storage | A1 | 1 |  |  | 1 | [13 empty] | 0 | Project Cost is $6M. Only #1M approved by Business Board on March 1st, 2004
Residence: | University College | A1A | 28 | 12.285 |  | 0.05 | 0 | 0 | 0 | 14.165 | 0 |  | 1.5 | [7 empty] | June 19th, 2003 BB approval: January 19th 2004 BB approval.
TOTAL | SECTION 1c: Total |  | 135.9764 | 54.2844 | 0 | 8.05 | 23.206 | 8.971 | 16 | 14.165 | 0 | 0 | 11.3
TOTAL | CURRENT CAPITAL PLAN |  | 811.4694 | 337.9604 | 0 | 104.9437 | 48.476 | 30.4366 | 22.9493 | 224.8244 | 0 | 0 | 41.88 |  |  |  | 446101
SECTION 3: FUTURE PROJECTS THAT WILL REQUIRE APPROVAL & FUNDING
Projects in Section 3 are of considerable importance to the University of Toronto. Many of these projects will require full external funding prior to formal approval to proceed. |  | Priority Unassigned | Project Cost Estimate | Fund Raising Targets [Estimates] |  | Enrolment Growth Funds | Student Levy |  |  | Increased borrowing |  |  | ACTION | Approved Expenditures to Date | [5 empty] | ADDITIOAL BORROWING | Notes
SECTOR | SECTION 3: ADDITIONAL PROJECT/ CURRENT CAPITAL PLAN
SECTION 3a: CLEAN-UP PROJECTS WITH FUNDING
UTSC: | Food Services | P | 2 |  |  | 1.46 |  |  |  | 0 |  |  | PROCEED | [7 empty] | Proceed: Ancillary contribution plus EGF of $1.46M
Arts & Science: | Ramsay Wright Laboratories | P | 0.7 |  |  | 0.7 |  |  |  | 0 |  |  | PROCEED | [6 empty] | 0 | Proceed: Use funding shown. Redefinition by Arts and Science.
| SECTION 3b: PRIORITY PROJECTS MOVING FORWARD with CONDITIONS | [8 empty] | 27
UTSC: | Science Renovations, Phase 2 Soils Laboratory Renovation | P | 1.08 | [17 empty] | Phase 2 of the UTSC Science Facilities
Health Sciences: | 155 College Street: Faculty of Nursing + Medicine | PA | 22.5 | [6 empty] | 18 |  |  | PROCEED | [6 empty] | 15.24 | Complete Project Committee Report. Investigate Government support. Security issues to be included
Other Faculties: | LIBRARY: Library Storage | P | 6 | [6 empty] | 6 |  |  | to BB in May 2004 | [6 empty] | 0 | $1M of the $6M project cost approved by BB on March 1st 2004. Additional $5M to be approved.
Campus: | Multi-Faith Centre | PA | 3 | 3 | [5 empty] | 3 |  |  | PROCEED | [6 empty] | 3 | Proceed with planning. Will require increased borrowing. Fund raising appears to be difficult.
SECTION 3c: PROJECTS ON HOLD, BUT NEED TO BE ADDRESSED
UTSC: | Science Facilities at UTSC [Phases 3 and 4] | P | 50 | [9 empty] | ON HOLD | [7 empty] | REQUIRES CFI SUPPORT with UTSC. Phase 3: Balcony Enclosure + Phase 4:Science Building
Arts & Science: | Math/Statistics/Anthropology; Post Medical Arts | P | 10 | [9 empty] | NEEDED/ OCGS | [6 empty] | 0 | NEED TO FIND MATH SPACE. CRITICAL
Arts & Science: | Medical Arts Building | P | 18 | [6 empty] | 18 |  |  | EXPLORATION | [6 empty] | 0 | Lease back exploration, cost for base reno is $11.5M.
Arts & Science: | Alternate: English top priority as borrowing space available | [11 empty] | EXPLORATION
SECTION 3d: PROJECTS WITH LEASE BACK REQUIREMENTS
UTSC: | Residence, Phase 5 | P | 27 | [16 empty] | 0 | Residence needs exist at UTSC
UTM: | Residence, Phase 8 | P | 27 | [16 empty] | 0 | Residence needs at UTM
SECTION 3e: FULL FUNDING REQUOIRED TO PROCEED
UTM: | South Building Renovations | P | 12 | [9 empty] | ON HOLD | [6 empty] | 0 | External funding will be needed. Post building of the Academic Learning Centre which opens in 2006
Arts & Science: | 1 Spadina Cres Renovation | PA | 35 | 35 | [8 empty] | NEEDED | [7 empty] | Full Funding required for renovation. Proceed with cleanup only for the present to house Fine Arts.
Other Faculties: | LIBRARY: Gertstein Sci. Info Centre. Balance of Gerstein Reno | P | [10 empty] | ON HOLD
Other Faculties: | Canadiana Building Renovation | P | [10 empty] | ON HOLD | [6 empty] | 0 | On Hold. Private Funding Needed for Public Policy School.
Other Faculties: | OISE-UT: Institute of Child Study [CS] | PA | 8 | 8 | [8 empty] | NEEDED | [6 empty] | 0 | Fund-raising on-going. Approved in Governance.
Other Faculties: | Rotman Building | PA | tba | [17 empty] | Project Committee active
Other Faculties: | LAW: Flavelle House, Phase 2 | PA | 68 | 68 | [15 empty] | 0 | $68M to be raised from external sources by the Faculty of Law
Other Faculties: | MUSIC: Johnson Building Renovation | PA | 30 | 30 | [16 empty] | $30M to be raised from external sources by Faculty of Music
Other Faculties: | Faculty of Landscape Architecture & Design | PA | 13 | 9 | [16 empty] | Original project was $13M. $4 now completed.
Campus: | Student Centre at St. George | P | 35 |  |  |  | 7 |  |  | 21 |  |  | ON HOLD | [6 empty] | 0 | Project on hold. Cost will depend on precise scope. University $7M; Levy $14M
Campus: | 255/257 College Street: Offices of V-P Business | P | 15 | [9 empty] | ON HOLD | [6 empty] | 0 | On Hold. Possible V-P Business Site.
Campus: | Hart House: Great Hall/Theatre/ Access | PA | [17 empty] | 0 | Proceeding with external funds
Campus: | Varsity Stadium & Arena | PA | 25 | [9 empty] | ON HOLD | [6 empty] | 0 | On Hold. 90 day investigation with Tanenbaum
Residence: | Innis College: Town Hall & Cinema Studies | PA | 5 | 5 | [8 empty] | ACTIVE | [6 empty] | 0 | Active. Innis has established what is required. Will proceed in phased appraoch as funding secured.
Residence: | New College: Student Centre | PA | [10 empty] | ON HOLD | [6 empty] | 0 | Input required from Office of Advancement
SECTOR | SECTION 4: INFRASTRUCTURE & DEFERRED MAINTENANCE
UTSC: | Infrastructure | P | 20 | [17 empty] | URGENT. Phased components
UTSC: | Deferred Maintenance | P | 27 | [17 empty] | Ongoing Issue
UTM: | Infrastructure | P | 20 | [17 empty] | URGENT. Under review.
UTM: | Deferred Maintenance | P | 16 | [17 empty] | Ongoing Issue
Campus: | Infrastructure | P | 20 | [17 empty] | Estimate.
Campus: | Deferred Maintenance | P | 276 | [17 empty] | Ongoing Issue
Page 3
Note on G32: R.D. Venter:11.04 = 6.38 + 4.66 12.24 =11.04 + 1.2
Note on I34: 50% Provost match + $0.875 allocation to UTSC project